## Payment Hub
ID | Work Item Type | Title | Test Step | Step Action | Step Expected | Area Path | Assigned To | State
466185 | Test Case | Manual Payments - Wires -REP Wires Same Day & Next Day - Payment Hub |  |  |  | OST\FIS Implementation - Agency Ops |  | Design
|  |  | 1 | Login to Payment Hub Test environment | User should be able to login to the URL and see the menu items - Payment Factory and Manual Payments | #VALUE!
|  |  | 2 | Left click on 'Manual payments' option. | The user should see menu options (inventories) for available payment types - checks, wires, ACH, Tax | #VALUE!
|  |  | 3 | Create a repetitive wire payment | Perform following steps to enter a wire payment: - click on Manually Created option under Wire Payments (ISO) section - in the screen to the right, right click and select "New Repetitive wire" for repetitive wire. This pops up a window with all available wire templates for your agency - select the right template and click ok at the bottom left of the screen. This will pop up the payemtn entry screen. Under general tab - enter all required fields: Under the 'General' tab enter the following mandatory fields - E2E (warrant number) - Effective date (same or next day) - Instructed amount - enter amount Under the 'Custom Fields' tab enter the following mandatory field: - Pay type - "C" for same day and "T" for next day wire. | #VALUE!
|  |  | 4 | Decision any exceptions - at entry | If there is an error on the payment, the transactions shows on the list with a red exclamation mark at the very left end in the "Manually created inventory" - click on the exclamation mark to see the type of error and make necessary updates: -Ex: Cutoff breached - the payment was entered for a date that was past the deadline - ex. same day wire entered after the deadline. You can open the payment, update the date to next day and pay type to 'T' and click ok.
|  |  | 5 | Approve payment - at entry | Once there are no Red exclamations ont eh entry, right click on it and select 'Accept'. This completes the entry process int eh "Manual Payments" section
|  |  | 6 | Left click on 'Payment factory' option. | The user that is authorized to approve payments should see this entry under 'Payment reception - To be approved by me' - right click on the transaction that needs to be approved and select approve payment. The user has the ability to reject or put the paymetn on hold at this stage if needed.
|  |  | 7 | Decision any errors - at approval | Decision any errors: - if the payment is not visible under to approve section, check the inventories under 'Exception handling' - if under Invalid - review the error (click red exclamation mark at the beginning of the entry on screen) and either cancel the entry or reaccept after correcting the error - if under screening areas (internal or external) - the user with screening approval roles can push them through - if under cutoff breached - user can select continue to proceed or reject or cancel payment. Once the payment is completed in this step then the agency is done with the manual entry. After this stage - the payment populates to OST's wire approval que for final approval. | #VALUE!
466186 | Test Case | Manual Payments - Wires -Non-REP Wires |  |  |  | OST\FIS Implementation - Agency Ops |  | Design
|  |  | 1 | Login to Payment Hub Test environment | User should be able to login to the URL and see the menu items - Payment Factory and Manual Payments | #VALUE!
|  |  | 2 | Left click on 'Manual payments' option. | The user should see menu options (inventories) for available payment types - checks, wires, ACH, Tax | #VALUE!
|  |  | 3 | Create a non-repetitive wire payment | Perform following steps to enter a wire payment: - click on Manually Created option under Wire Payments (ISO) section - in the screen to the right, right click and select "New wire" for non-repetitive wire. This pops up a payment entry window Under general tab - enter all required fields: Under the 'General' tab enter the following mandatory fields - Data owner - should auto populate your agency number unless you have access to multiple agencies, in which case select the required agency from drop down menu - E2E (warrant number) - Effective date - Instructed amount - enter amount, ALWAYS USD in the field next to amount - Debtor account\Static Data Account - agency clearing account - 21AAA00. This selection populates all the other mandatory fields under Debtor side of the screen. - Creditor account\Account number - payee's bank account number - Creditor\Name - Payee name - Creditor\Line 3/Country - Country code - Creditor agent\BIC - payee bank's routing number - Creditor\Line3/Country - country code Under the 'Custom Fields' tab enter the following mandatory field: - Class Cd - ASA etc. - Pay type - "C" for same day and "T" for next day wire. | #VALUE!
|  |  | 4 | Decision any exceptions - at entry | If there is an error on the payment, the transactions shows on the list with a red exclamation mark at the very left end in the "Manually created inventory" - click on the exclamation mark to see the type of error and make necessary updates: -Ex: Cutoff breached - the payment was entered for a date that was past the deadline - ex. same day wire entered after the deadline. You can open the payment, update the date to next day and pay type to 'T' and click ok.
|  |  | 5 | Approve payment - at entry | Once there are no Red exclamations on the entry, right click on it and select 'Accept'. This completes the entry process in the "Manual Payments" section
|  |  | 6 | Left click on 'Payment factory' option. | The user that is authorized to approve payments should see this entry under 'Payment reception - To be approved by me' - right click on the transaction that needs to be approved and select approve payment. The user has the ability to reject or put the payment on hold at this stage if needed.
|  |  | 7 | Decision any errors - at approval | Decision any errors: - if the payment is not visible under to approve section, check the inventories under 'Exception handling' - if under Invalid - review the error (click red exclamation mark at the beginning of the entry on screen) and either cancel the entry or reaccept after correcting the error - if under screening areas (internal or external) - the user with screening approval roles can push them through - if under cutoff breached - user can select continue to proceed or reject or cancel payment. Once the payment is completed in this step then the agency is done with the manual entry. After this stage - the payment populates to OST's wire approval que for final approval. | #VALUE!
466187 | Test Case | Manual Payments - Checks and Issue records - Payment Hub |  |  |  | OST\FIS Implementation - Agency Ops |  | Design
|  |  | 1 | Login to Payment Hub Test environment | User should be able to login to the URL and see the menu item "Manual Payments" | #VALUE!
|  |  | 2 | Left click on 'Manual Payments' option. | The user should see display of all menu options (inventories) available to the user | #VALUE!
|  |  | 3 | Create a check payment - paper check to be printed either at OST or remote (use pay type P) or issue record for checks already created at agency (use pay type W) | Right click in the screen to the right and select "new". Enter payment details: details are required under two different sections - General and Custom Fields. General tab: -Data owner - should auto populate your agency number unless you have access to multiple agencies, in which case select the required agency from drop down menu - ex. 74000) - E2E (Warrant number) - warrant number - Req. exec. date - issue date for the check - Instructed amount - amount; always USD (in the box next to amount - Debtor account\Static Data account - account number from which check is issued - Ex. 21AAA00 where AAA is agency number. Use drop down to selct the clearing account etc. to issue the check out of. This auto populates the fields under the Debtor section. - Creditor\Name - enter payee name and country - ALWAYS US Custom Fileds tab: - Class code - enter the class code - ASA - Pay Type - P for checks to be printed and W for issue records Once completed - click OK | #VALUE!
|  |  | 4 | Edit/Approve the entered transaction | In order to complete the entry from the step above, please select the transaction and right click. Make the selection - accept, delete, edit etc. Once accepted - the entry moves to the next step in the process flow.
|  |  | 5 | Approval in Payment factory | The user (with approval role) should be able to approve the manual entry in payment factory: - left click on "Payment Factory" - Under 'Payment reception" - click on "To be approved by me". This should populate a list of available entries on the screen to the right - left clcik on the entry to approve and select required action - approve, put on hold, reject | #VALUE!
|  |  | 6 | Decision any errors - at approval | Decision any errors: - if the payment is not visible under to approve section, check the inventories under 'Exception handling' - if under Invalid - review the error (click red exclamation mark at the beginning of the entry on screen) and either cancel the entry or reaccept after correcting the error - if under screening areas (internal or external) - the user with screening approval roles can push them through Once the payment is completed in this step then the agency is done with the manual entry.
466188 | Test Case | Manual Payments - ACH - Payment Hub |  |  |  | OST\FIS Implementation - Agency Ops |  | Design
|  |  | 1 | Login to Payment Hub Test environment | User should be able to login to the URL and see the menu items - Payment Factory and Manual Payments | #VALUE!
|  |  | 2 | Left click on 'Manual payments' option. | The user should see menu options (inventories) for available payment types - checks, wires, ACH, Tax | #VALUE!
|  |  | 3 | Create an ACH payment (pay type E) | Perform following steps to enter an ACH payment: - click on Manually Created option under Local formats-ACH Payments (ISO) section - in the screen to the right, right click and select "New". This pops up the payment entry screen. - Under the 'General' tab enter the following mandatory fields - Data owner - this should auto populate your agency number unless you have access to multiple agencies in which case please select the right agency from the drop down menu. - E2E (warrant number) - Effective date (can't be past date, can go 30 calendar days into future) - Instructed amount - enter USD in the field next to it if it doesn't auto populate - Debtor account - account number - click the magnifying glass next to 'Static data account' and select the right agency account from the menu.- ex. 21AAA00 (where AAA is agency number). This should auto populate the fields required under Debtor account and Debtor sections. - In the Creditor account section - click the magnifying glass next to 'From template' and select the right participant ID. You can filter the list by right clicking the column header and including the filter value between two %%s. Click on the right participant and click ok. This should populate the remaining required fields in the creditor section. - Under the 'Custom Fields' tab enter the following mandatory field: - Pay type - always "E" - manual ACH payments are allowed only for existing participants in the system. - enter the required class code - this value can be obtained from the participant ID fields - Ex. RFD, RET,ASA etc. Once the Red exclamation marks next to the General and Custom fields tabs disappear (which means all mandatory fields have been entered) click ok to accept the payment. | #VALUE!
|  |  | 4 | Decision any errors - at entry | If the payment pops up on the screen to the right with a Red exclamation at the very left end, then there is an error on the entry. - click on the red exclamation to see the error. Common errors are invalid dates and cutoff breaches (when payment was entered after the deadline). For invalid dates, double click the entry and update the date and click ok. For cutoff breach - you can update the date on the entry and click ok or right click not eh entry and select accept. If accepted, the system will recalculate the date to the next business day. At this point the transaction has left the manual entry screen and moved to 'payment factory' area for further processing | #VALUE!
|  |  | 5 | Left click on 'Payment factory' option. | The user that is authorized to approve payments should see this entry under 'Payment reception - To be approved by me' - right click on the transaction to approve and select approve payment. The user has the ability to reject the payment as well as needed. | #VALUE!
|  |  | 6 | Decision any errors - at approval | Decision any errors: - if the payment is not visible under to approve section, check the inventories under 'Exception handling' - if under Invalid - review the error (click red exclamation mark at the beginning of the entry on screen) and either cancel the entry or reaccept - if under screening areas - the user with screening approval roles can push them through - if under cutoff breached - user can select continue to proceed or reject or cancel payment. Once the payment is completed in this step then the agency is done with the manual entry. | #VALUE!
466189 | Test Case | Manual Payments - ACH - TAX payments - Payment Hub |  |  |  | OST\FIS Implementation - Agency Ops |  | Design
|  |  | 1 | Login to Payment Hub Test environment | User should be able to login to the URL and see the menu items - Payment Factory and Manual Payments | #VALUE!
|  |  | 2 | Left click on 'Manual payments' option. | The user should see menu options (inventories) for available payment types - checks, wires, ACH, Tax | #VALUE!
|  |  | 3 | Create an TAX payment (pay type E) | Perform following steps to enter an ACH payment: - click on Manually Created option under Local formats-Tax Payments (ISO) section - in the screen to the right, right click and select "New Tax Payment". This pops up the payment entry screen. Tax entries require data in three different tabs - General, Custom Fields, and Tax. - Under the 'General' tab enter the following mandatory fields - Data owner - this should auto populate your agency number unless you have access to multiple agencies in which case please select the right agency from the drop down menu. - E2E (warrant number) - Effective date (can't be past date, can go 30 calendar days into future) - Instructed amount - enter amount and enter USD in the field next to it - Debtor account\Static data account - click the magnifying glass next to this field and select the agency account from the menu.- ex. 21AAA00 or 7FFFAAA (where AAA is agency and FFF is fund number). This should auto populate the fields required under Debtor account and Debtor sections. - Creditor account\From template - click the magnifying glass next to this field and select the required participant ID. You can filter the list by right clicking the column header and including the filter value between two %%s. Click on the right participant and click ok. This should populate the remaining required fields in the creditor section. - Under the 'Custom Fields' tab enter the following mandatory field: - Pay type - always "E" - manual ACH payments are allowed only for existing participants in the system. - enter the required class code - this value can be obtained from the participant ID fields - IRS, TXS, or TXW Under the Tax tab: - Tax type - select the appropriate tax type from drop down menu - Tax Date Once the Red exclamation marks next to the General, Custom fields, and Tax tabs disappear (which means all mandatory fields have been entered) click ok to accept the payment. | #VALUE!
|  |  | 4 | Decision any errors - at entry | If the payment pops up on the screen to the right with a Red exclamation at the very left end, then there is an error on the entry. - click on the red exclamation to see the error. Common errors are invalid dates and cutoff breaches (when payment was entered after the deadline). For invalid dates, double click the entry and update the date and click ok. For cutoff breach - you can update the date on the entry and click ok or right click on the entry and select Accept. If accepted, the system will recalculate the date to the next business day. At this point the transaction has left the manual entry screen and moved to 'payment factory' area for further processing | #VALUE!
|  |  | 5 | Left click on 'Payment factory' option. | The user that is authorized to approve payments should see this entry under 'Payment reception - To be approved by me' - right click on the transaction to approve and select approve payment. The user has the ability to reject the payment as well as needed. | #VALUE!
|  |  | 6 | Decision any errors - at approval | Decision any errors: - if the payment is not visible under to approve section, check the inventories under 'Exception handling' - if under Invalid - review the error (click red exclamation mark at the beginning of the entry on screen) and either cancel the entry or reaccept - if under screening areas - the user with screening approval roles can push them through - if under cutoff breached - user can select continue to proceed or reject or cancel payment. Once the payment is completed in this step then the agency is done with the manual entry. This payment is now queued for OST approval | #VALUE!